## GPN_UNGUJA
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES - EXTERNAL USE
NAME OF PROCURING AND DISPOSAL ENTITY: ZANZIBAR ELECTORAL COMMISSION (ZEC) - UNGUJA
FINANCIAL YEAR : 2023/2024
Description | Tender No. | Number of lots | Procurement Method | PRE - QUALIFICATION |  |  | INVITATION AND AWARD OF BIDS
|  |  |  | Invitation Date | Closing-Opening | Notification of Applicants | Bid Invitation Date | Bid Closing-Opening | Award Notification Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
GOODS
Procurement of Stationary | SMZ/303/G/MV/2023/24/01 | 1 | MV | N/A | N/A | N/A | 2023-08-09 | 2023-08-14 | 2023-08-21
Procurement of Diesel fuel | SMZ/303/G/DP/2023/24/02 | 1 | DP | N/A | N/A | N/A | 2023-08-09 | 2023-08-14 | 2023-08-21
Procurement of ICT Equipment and Accessories | SMZ/303/G/MV/2023/24/03 | 1 | MV | N/A | N/A | N/A | 2023-08-09 | 2023-08-14 | 2023-08-21
Procurement of Cleaning materials | SMZ/303/G/MV/2023/24/04 | 1 | MV | N/A | N/A | N/A | 2023-08-16 | 2023-08-23 | 2023-08-30
Procurement of Domestic Applience (Curtain / Fitting) | SMZ/303/G/MV/2023/24/05 | 1 | MV | N/A | N/A | N/A | 2023-08-16 | 2023-08-23 | 2023-08-30
Procument of Office Furniture | SMZ/303/G/MV/2023/24/06 | 1 | OQ | N/A | N/A | N/A | 2023-08-17 | 2023-08-31 | 2023-09-20
Procurement of spare parts for Services, repair and Maintenance of Motor Vehicle | SMZ/303/G/OQ/2023/24/07 | 1 | OQ | N/A | N/A | N/A | 2023-08-17 | 2023-08-31 | 2023-09-20
NON CONSULTANCY
Provision of Transport and Ticketing | SMZ/303/NC/NCB/2023/24/08 | 1 | NCB | N/A | N/A | N/A | 2023-08-17 | 2023-09-07 | 2023-09-27
Provision of Food and Refreshment | SMZ/303/NC/OQ/2023/24/09 | 1 | OQ | N/A | N/A | N/A | 2023-08-17 | 2023-08-31 | 2023-09-20
WORKS
Construction and Upgrading of Minor Civil Works | SMZ/303/W/MV/2023/24/10 | 1 | MV | N/A | N/A | N/A | 2023-08-23 | 2023-08-28 | 2023-09-04
Major Maintenance of Building | SMZ/303/W/OQ/2023/24/11 | 1 | OQ | N/A | N/A | N/A | 2023-08-17 | 2023-09-07 | 2023-09-27
KEY : | NCB _ NATIONAL COMPETITTIVE BIDDING |  |  |  |  | KEY APPROACH : |  | OPEN
| ICB _ INTERNATIONAL COMPETITTIVE BIDDING | [6 empty] | SELECTIVE
| MV _ MINOR VALUE | [6 empty] | SINGLE SOURCE
DP _ DIRECT PROCUREMENT
OQ _ OPEN QUOTATION

## GPN_PEMBA
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES - EXTERNAL USE
NAME OF PROCURING AND DISPOSAL ENTITY: ZANZIBAR ELECTORAL COMMISSION (ZEC) - PEMBA
FINANCIAL YEAR: 2023/2024
Description | Tender No. | Number of lots | Procurement Method | PRE - QUALIFICATION |  |  | INVITATION AND AWARD OF BIDS
|  |  |  | Invitation Date | Closing-Opening | Notification of Applicants | Bid Invitation Date | Bid Closing-Opening | Award Notification Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
GOODS
Procurement of Stationary | SMZ/303/G/MV/2023/24/01 | 1 | MV | N/A | N/A | N/A | 2023-08-09 | 2023-08-14 | 2023-08-21
Procurement of Diesel fuel | SMZ/303/G/MV/2023/24/02 | 1 | MV | N/A | N/A | N/A | 2023-08-09 | 2023-08-14 | 2023-08-21
Procurement of ICT Equipment and Accessories | SMZ/303/G/MV/2023/24/03 | 1 | MV | N/A | N/A | N/A | 2023-08-09 | 2023-08-14 | 2023-08-21
Procurement of Cleaning material. | SMZ/303/G/MV/2023/24/04 | 1 | MV | N/A | N/A | N/A | 2023-08-16 | 2023-08-21 | 2023-08-28
Procurement of Staff Uniforms | SMZ/303/G/MV/2023/24/05 | 1 | MV | N/A | N/A | N/A | 2023-08-16 | 2023-08-21 | 2023-08-28
Procument of Furniture | SMZ/303/G/MV/2023/24/06 | 1 | MV | N/A | N/A | N/A | 2023-08-16 | 2023-08-21 | 2023-08-28
Procurement of spare parts for Services, repair and Maintenance of Motor Vehicle | SMZ/303/G/MV/2023/24/07 | 1 | MV | N/A | N/A | N/A | 2023-08-23 | 2023-08-28 | 2023-09-04
NON CONSULTANCY
Provision of Transport and Ticketing | SMZ/303/NC/MV/2023/24/08 | 1 | MV | N/A | N/A | N/A | 2023-08-23 | 2023-08-28 | 2023-09-04
WORKS
Construction and Upgrading of Minor Civil Works | SMZ/303/W/MV/2023/24/09 | 1 | MV | N/A | N/A | N/A | 2023-08-23 | 2023-08-28 | 2023-09-04
KEY : | NCB _ NATIONAL COMPETITTIVE BIDDING |  |  |  |  | KEY APPROACH : |  | OPEN
| ICB _ INTERNATIONAL COMPETITTIVE BIDDING | [6 empty] | SELECTIVE
| MV _ MINOR VALUE | [6 empty] | SINGLE SOURCE
DP _ DIRECT PROCUREMENT
OQ _ OPEN QUOTATION